## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | Customer Registration | As a customer, I want to open customer registration page and save the entered customer details. | Task#1 | Access the homepage | High | Abhijeet | 18/3/19 | 18/3/19 | 2 |  | Done | Admin registration is excluded. Admin data is manually saved in the database.
|  |  |  | Task#2 | Redirect to UserRegistration Page | High | Vansh | 18/3/19 | 19/3/19 | 5 |  | Done | Pan and Adhaar Field have unique constraint
|  |  |  | Task#3 | User Registration Field Validation | Medium | Anuj | 18/3/19 | 18/3/19 | 2 |  | Done | We have taken username as the primary key instead of userId.
|  | Vendor Registration | As a customer, I want to open customer registration page and save the entered customer details. | Task#4 | Create a registeration JSP page to accept the data from vendor as per the field of vendor table. | High | Saurabh | 18/3/19 | 18/3/19 | 2 |  | Done | We have taken vendorName as the primary key for vendor table.
|  |  |  | Task#5 | Create VendorEntity class, Vendor DAO and Vendor Service class to insert the vendor data and controller and verify on backend. | High | Chirag | 18/3/19 | 19/3/19 | 5 |  | Done | Changed Email Address length to 30.
|  |  |  | Task#6 | Integrate the code and verify its working . | High | Anuj | 20/3/19 | 21/3/19 | 5 |  | Done | Password field length is changed to 100 characters.
| #2 | Bill Payment | As a customer, I want to pay the required amount for a particular type of bill. | Task#7 | Create a bill payment page containing the different types of bills that user can pay. | High | Saurabh | 25/03/19 | 31/03/19 | 8 |  | Done
|  |  |  | Task#8 | Create a bill information page for each type of bill, containing the required details that user need to fill. | High | Chirag | 25/03/19 | 31/03/19 | 8 |  | Done
|  |  |  | Task#9 | Create a vendor information page for each type of vendor, contaning the required details that user need to fill | High | Abhijeet | 25/03/19 | 31/03/19 | 8 |  | Done | We have included vendor details page in the bill details form.
|  |  |  | Task#10 | Create bill controller class, bill DAO class, bill entity class and bill Service class. | High | Anuj | 25/03/19 | 31/03/19 | 8 |  | Done | We have excluded payment reminder requirement due to technical issues.
|  |  |  | Task#11 | Integrate the code and verify its working. | High | Vansh | 25/03/19 | 31/03/19 | 8 |  | Done
| #3 | Bill Mapping | As a customer, I want to record the details of the form for a bill and set a reminder to pay the bill. | Task#12 | Create a bill payment page containing the different types of bills that user can record. | Low | Chirag | 2019-01-04 | 2019-05-04 | 8 |  | Done | We have excluded helpline requirement. Instead of that we have provided contactUs page.
|  |  |  | Task#13 | Create a page that would display the list of all pending bills of the particular type of bill for a user. | Low | Abhijeet | 2019-01-04 | 2019-05-04 | 8 |  | Done
|  |  |  | Task#14 | Create a bill information page for each type of bill, containing the required details that user need to fill. | Low | Saurabh | 2019-01-04 | 2019-05-04 | 8 |  | Done
|  |  |  | Task#15 | Modify the bill controller,bill DAO and bill Service class, so that the recorded bill is saved in the database | Low | Vansh | 2019-01-04 | 2019-05-04 | 8 |  | Done
|  |  |  | Task#16 | Integrate the code and verify its working. | Low | Anuj | 2019-01-04 | 2019-05-04 | 8 |  | Done